## Fibonacci Points w User Stories
Med-X User Stories
| As a [description of user] |  |  | Legend:
| I want [functionality] |  |  | will be done in Sprint 2
| So that [benefit] |  |  | will be done in Sprint 3
will be done in Sprint 4
Estimation | User ID | As a | I want | So that | Feature
3 | 1 | Radiologist | to easily upload x-ray images | doctors and patients have access to the images | Image Upload
3 | 2 | Doctor | to easily upload x-ray images | doctors and patients have access to the images | Image Upload
3 | 3 | Patient | to easily upload x-ray images from my personal machine | doctors have access to the images for review | Image Upload
13 | 4 | Radiologist | to provide quick and automated x-ray results for common chest health issues | more time can be dedicated to analyze uncommon chest health issues | Medexer (AI)
13 | 5 | Doctor | to provide quick and automated x-ray results for common chest health issues | patient response rate and physician workflow improves | Medexer (AI)
8 | 6 | Doctor | to add comments to patient x-ray results | patients are informed early about other information the result does not provide | Doctor Notes
5 | 7 | Patient | to view whether a doctor has reviewed my x-ray results | I can be more confident about the verified results | Reviewed Status
2 | 8 | Patient | my x-ray results to be explained in simpler terms | I can better understand my diagnosis and health issue | Result Description
1 | 9 | Doctor | to download patient x-ray reports | I can store patient records locally | Download Report
1 | 10 | Patient | to download my x-ray reports | I can store my records locally | Download Report
5 | 11 | Patient | to have access to all of my x-ray report history | I can track my chest health issues | Report History
5 | 12 | Doctor | to have access to all patient x-ray report histories | I can track patient chest health issues | Report History
2 | 13 | Patient | to quickly view my latest x-ray report | my most recent information is easily accessible | Dashboard
5 | 14 | Patient | to be notified once there is a change to my reports (upload, review, notes, etc.) | I can be informed about any updates as soon as possible | Notification
5 | 15 | Doctor | to be notified once there is a change to patient reports (upload, report, etc.) | I can be informed about any updates as soon as possible | Notification
8 | 16 | Doctor | to browse a specific report and record | I can quickly locate specified information | Search
8 | 17 | Patient | to browse a specific report and record | I can quickly locate specified information | Search
3 | 18 | Radiologist | to register and store my personal info (ID, name, D.O.B.) in my own account | I can access patient information and connect with patients and doctors privately | Profile
3 | 19 | Doctor | to register and store my personal info (ID, name, D.O.B.) in my own account | I can access patient information and connect with patients and radiologists privately | Profile
3 | 20 | Patient | to register and store my personal info (ID, name, D.O.B.) in my own account | I can access my medical information and connect with doctors privately | Profile
3 | 21 | Patient | to login and logout of my own account | my medical information, records and reports are secure | Login/Logout
3 | 22 | Doctor | to login and logout of my own account | patient medical information, records and reports are secure | Login/Logout
3 | 23 | Patient | to login using my e-mail address | I can access my medical information, records and reports | Login/Logout
3 | 24 | Doctor | to login using my medical professional id number | I can access patient medical information, records and reports | Login/Logout
1 | 25 | Patient | update my personal information such as my name, address, phone number, etc | the portal has up-to-date information in the event I need to be reached urgently | Profile